## Task Backlog
ID | Category | Task | Description | Best Practice Ref | Priority | Effort (Days) | Impact (1-5) | Feasibility (1-5) | Score | Phase | Status | Dependencies | Owner | Notes
ML-01 | Micro Loop | Design "Survey Run" pre-level mechanic | 30-second train flyover that reveals terrain/cities before each level starts, delivering instant visual reward | BP#1: First Fun | Critical | 5 | 5 | 4 | 20 | Phase 1 | Not Started | - |  | Key D1 retention driver
ML-02 | Micro Loop | Design track-laying puzzle mini-game | Quick puzzle: connect two cities with minimum cost track. Earns starting bonus. Teaches core mechanic in 60s | BP#1: First Fun | Critical | 8 | 5 | 3 | 15 | Phase 1 | Not Started | - |  | Alternative to ML-01; pick one or both
ML-03 | Micro Loop | Pre-place starter train on Levels 1-5 | First 5 levels begin with a running train on a short route so players see revenue ticking before they build anything | BP#1: First Fun | Critical | 3 | 5 | 5 | 25 | Phase 1 | Not Started | - |  | Lowest effort, highest impact first-fun fix
ML-04 | Micro Loop | Redesign first 60 seconds of Level 1 | Full FTUE redesign: player sees train running → prompted to expand route → instant positive feedback | BP#1: First Fun | Critical | 5 | 5 | 4 | 20 | Phase 1 | Not Started | ML-03 |  | Depends on ML-03 being implemented first
EC-01 | Economy | Introduce premium currency (Gold Rivets) | Rare currency earned via achievements/milestones, purchasable $0.99-$4.99. Spent on cosmetics, RP boosters, convenience | BP#2: Dual Currency | High | 10 | 5 | 3 | 15 | Phase 1 | Not Started | - |  | Core monetization enabler
EC-02 | Economy | Design faucet-drain balance model | Spreadsheet model mapping all soft ($), hard (Rivets), and RP sources/sinks with target ratios per chapter | BP#2: Dual Currency | High | 5 | 4 | 4 | 16 | Phase 1 | Not Started | EC-01 |  | Use Machinations or spreadsheet sim
EC-03 | Economy | Resolve cross-document number inconsistencies | Fix starting funds ($5K-$15K vs $30K-$70K), RP values (20/35/50 vs 40/70/100), mountain cost (3x vs 4x), hex orientation | GDD Review §8 | Critical | 2 | 4 | 5 | 20 | Phase 1 | Not Started | - |  | Block other economy work until resolved
EC-04 | Economy | Soften maintenance era scaling | Change 1.5x per-era multiplier to 1.2x OR decouple from time and tie to player tech choices | GDD Review §3 | Medium | 3 | 3 | 5 | 15 | Phase 2 | Not Started | EC-03 |  | Reduces punishment for slow players
EC-05 | Economy | Increase train retirement refund | Raise from 25% to 40-50% refund, at least in Chapter 1. Reduces punishment for misclicks on mobile | GDD Review §3 | Medium | 1 | 3 | 5 | 15 | Phase 1 | Not Started | - |  | Quick win, big UX improvement
EC-06 | Economy | Make T1 upgrades more impactful | Reduce cost to 30-40 RP OR increase effect to 20-25%. First purchase must feel like a power-up, not a rounding error | GDD Review §4 | High | 2 | 4 | 5 | 20 | Phase 1 | Not Started | - |  | Critical for meta-loop first impression
MN-01 | Monetization | Design Engineer's Pass (Season Pass) | $1.99/month: 2x RP, exclusive train skin, 3 bonus levels, profile badge. Non-pay-to-win recurring revenue | BP#3: Time Compression | High | 8 | 5 | 3 | 15 | Phase 2 | Not Started | EC-01 |  | Primary recurring revenue stream
MN-02 | Monetization | Deepen cosmetic catalog | Expand from ~$10 ceiling to $30+: more train skins, animated effects, station themes, conductor avatars, trail effects | BP#3: Time Compression | High | 12 | 4 | 3 | 12 | Phase 2 | Not Started | - |  | Current catalog too thin for sustainability
MN-03 | Monetization | Design Gold Rivets IAP bundles | Starter Pack ($0.99), Weekly Deal ($1.99), Value Pack ($4.99). Include rivets + cosmetic preview to drive conversion | BP#3: Time Compression | High | 5 | 5 | 4 | 20 | Phase 2 | Not Started | EC-01 |  | Bridge between free play and spending
MN-04 | Monetization | Revise revenue projections | Lower conversion assumption from 25% to 3-5%. Model revenue with Season Pass + Rivets + cosmetics as primary drivers | GDD Review §5 | High | 3 | 3 | 5 | 15 | Phase 1 | Not Started | - |  | Current projections are 5x too optimistic
SD-01 | Session Design | Add passive Railway Network (idle RP) | Completed levels contribute to persistent network on Meta Hub. Generates 1-3 RP/hour, collected on app open | BP#6: Multi-Cadence | High | 8 | 5 | 3 | 15 | Phase 2 | Not Started | - |  | Creates between-session check-in reason
SD-02 | Session Design | Design daily bonus check-in flow | 24-hour reset: claim RP, see daily challenge, check network earnings. Target: 30-second session | BP#6: Multi-Cadence | Medium | 5 | 4 | 4 | 16 | Phase 2 | Not Started | SD-01 |  | Drives multi-session habit
SD-03 | Session Design | Add Builder's Log notification | On app open: summary of offline events (network RP earned, daily challenge available, upgrade of the day) | BP#6: Multi-Cadence | Medium | 4 | 3 | 4 | 12 | Phase 2 | Not Started | SD-01 |  | Makes reopening the app feel rewarding
SD-04 | Session Design | Implement Upgrade of the Day rotation | One random upgrade at 30% discount each day in Upgrade Hub. Creates urgency without FOMO dark pattern | BP#6: Multi-Cadence | Low | 3 | 2 | 4 | 8 | Phase 3 | Not Started | - |  | Light engagement hook
SO-01 | Social | Add async ghost rivals on level replay | When replaying, show ghost timeline of player's best run (or friend's). Zero server cost, works offline | BP#4: Social Systems | High | 6 | 4 | 4 | 16 | Phase 2 | Not Started | - |  | Best effort-to-impact social feature
SO-02 | Social | Implement Endless Mode weekly leaderboard | GameCenter / Google Play Games integration. Weekly reset, top-revenue ranking. Designed but not built | BP#4: Social Systems | High | 5 | 4 | 3 | 12 | Phase 2 | Not Started | - |  | Already in PROGRESSION.md, just needs building
SO-03 | Social | Add 3-star win share screenshot | Auto-generate shareable image on 3-star completion with game branding. Free UA / social proof | BP#4: Social Systems | Medium | 4 | 3 | 4 | 12 | Phase 2 | Not Started | - |  | Free marketing channel
SO-04 | Social | Design community weekly challenge | All players share a level seed, compete on time/revenue via async leaderboard. Reward: bonus RP + badge | BP#4: Social Systems | Medium | 8 | 4 | 3 | 12 | Phase 3 | Not Started | SO-02 |  | Requires leaderboard infra first
SO-05 | Social | Design alliance-lite system | Small co-op groups with shared RP pool bonuses, cooperative challenge targets. No chat, no real-time | BP#4: Social Systems | Low | 15 | 4 | 2 | 8 | Phase 3 | Not Started | SO-02 |  | Only if game succeeds; high effort
VR-01 | Variable Rewards | Add bonus RP roll on level complete | Post-level wheel/card flip: 0-30 bonus RP (EV ~10). Adds surprise to every completion without feeling manipulative | BP#9: Variable Rewards | Medium | 4 | 4 | 5 | 20 | Phase 2 | Not Started | - |  | Simple to build, meaningful engagement lift
VR-02 | Variable Rewards | Design random in-level events | 2-3 event types: resource boom (+50% revenue tile), track grant (free segment), bonus city appears. 10-15% chance per level | BP#9: Variable Rewards | Medium | 6 | 4 | 3 | 12 | Phase 2 | Not Started | - |  | Makes each playthrough feel different
VR-03 | Variable Rewards | Add daily mystery chest | Login reward: small chest with random cosmetic shard OR RP bonus OR Gold Rivet. Drives daily open | BP#9: Variable Rewards | Medium | 3 | 3 | 4 | 12 | Phase 2 | Not Started | EC-01 |  | Requires premium currency system first
LO-01 | LiveOps | Build Daily Challenge system | Already fully designed in PROGRESSION.md. Implement: speed runs, minimalist, train limit, no demolish, star hunt | BP#7: Event-Driven | High | 8 | 4 | 4 | 16 | Phase 2 | Not Started | - |  | Designed but not coded; highest-priority event
LO-02 | LiveOps | Design monthly seasonal theme system | Visual theme swap (autumn, winter, spring) with themed challenge set and exclusive cosmetic reward per season | BP#7: Event-Driven | Medium | 10 | 3 | 3 | 9 | Phase 3 | Not Started | LO-01, MN-02 |  | Requires cosmetic catalog depth
LO-03 | LiveOps | Design quarterly season reset + pass content | Season Pass content rotation, leaderboard reset, season-exclusive train skin. Drives recurring engagement | BP#7: Event-Driven | Medium | 8 | 3 | 2 | 6 | Phase 3 | Not Started | MN-01, LO-01 |  | Requires Season Pass infrastructure
LO-04 | LiveOps | Create LiveOps content calendar template | 12-month calendar of events: daily, weekly, seasonal, limited. Plan content pipeline for post-launch | BP#7: Event-Driven | Medium | 3 | 3 | 5 | 15 | Phase 2 | Not Started | - |  | Planning artifact, not code
OB-01 | Onboarding | Redesign FTUE with progressive disclosure | Hide tech tree, research, and advanced tools for first 15 min. Reveal systems one at a time over first hour | BP#8: Progressive Disclosure | High | 6 | 5 | 4 | 20 | Phase 1 | Not Started | ML-03 |  | Current design shows full UI immediately
OB-02 | Onboarding | Add Meta Hub onboarding tour | Post-Level-1 guided tour: highlight Upgrade Hub, explain RP, walk through first upgrade purchase | GDD Review §6 | High | 4 | 4 | 5 | 20 | Phase 1 | Not Started | - |  | Currently no guidance for upgrade system
OB-03 | Onboarding | Define haptic feedback events | Light tap: hex select. Medium: track place. Heavy: train purchase. Success: level complete. Warning: bankruptcy near | GDD Review §6 | Medium | 3 | 3 | 5 | 15 | Phase 1 | Not Started | - |  | Capacitor Haptics already in dependencies
OB-04 | Onboarding | Design notification queue for mobile | Replace 1-toast-at-2.5s with sequential queue + bell icon log. Prevents missing 80% of delivery notifications | GDD Review §6 | Medium | 4 | 3 | 4 | 12 | Phase 1 | Not Started | - |  | Important for information clarity
LD-01 | Level Design | Design Chapter 2 in full detail | Complete level configs for all 12 levels: starting funds, time limits, star conditions, map seeds. This is the conversion chapter | GDD Review §7 | Critical | 8 | 5 | 4 | 20 | Phase 1 | Not Started | EC-03 |  | Paywall chapter must be best-designed content
LD-02 | Level Design | Expand objective variety | Add efficiency, time-pressure, and scenario objectives beyond connect/earn. At least 3 new objective types for Ch2-5 | GDD Review §7 | High | 6 | 4 | 4 | 16 | Phase 2 | Not Started | LD-01 |  | 5 types across 60 levels will feel repetitive
LD-03 | Level Design | Design optional Casual Mode | Toggle: remove time limits, soften bankruptcy. Tradeoff: max 1-star. Expands audience without diluting challenge | GDD Review §7 | Medium | 4 | 3 | 5 | 15 | Phase 2 | Not Started | - |  | Accessibility feature, low effort
LD-04 | Level Design | Add intermediate career rank | Insert rank at 15-18 levels between Track Foreman (10) and Railway Manager (25). Gap is too large currently | GDD Review §4 | Low | 1 | 2 | 5 | 10 | Phase 2 | Not Started | - |  | Quick fix, smooths progression pacing
LD-05 | Level Design | Design prestige/reset mechanic | Optional campaign reset for cosmetic rewards + small permanent bonus. Gives completionists a long-tail loop | GDD Review §4 | Low | 6 | 3 | 3 | 9 | Phase 3 | Not Started | - |  | Only relevant once all 60 levels exist
AI-01 | Analytics | Define analytics event plan | Key events: level_start, level_complete, star_earned, rp_spent, train_purchased, session_length, funnel_step, iap_triggered | GDD Review §9 | High | 4 | 4 | 5 | 20 | Phase 1 | Not Started | - |  | Cannot optimize what you don't measure
AI-02 | Analytics | Design A/B test framework for economy | Test starting funds, RP amounts, upgrade costs, train refund %. Need at least 2 cohorts for Ch1 economy tuning | GDD Review §9 | Medium | 5 | 3 | 3 | 9 | Phase 2 | Not Started | AI-01 |  | Requires analytics pipeline first
AI-03 | Analytics | Implement auto-save and recovery | Define save frequency (every in-game month?), recovery flow on crash, state validation on load | GDD Review §9 | Medium | 4 | 3 | 4 | 12 | Phase 1 | Not Started | - |  | Critical for mobile where interruptions are frequent
AI-04 | Analytics | Plan localization pipeline | String extraction, translation workflow, RTL support assessment. Priority markets: Japan, Korea, Germany, France | GDD Review §9 | Low | 5 | 3 | 3 | 9 | Phase 3 | Not Started | - |  | Revenue unlock for international markets

## Dashboard
Iron Dominion — Implementation Dashboard
Total Tasks | Critical | High | Medium | Low | Total Effort (Days)
43 | 6 | 15 | 17 | 5 | 232
Tasks by Category
Category | Count | Effort (Days) | Avg Score
Micro Loop | 4 | 21 | 20
Economy | 6 | 23 | 16.8333
Monetization | 4 | 28 | 15.5
Session Design | 4 | 20 | 12.75
Social | 5 | 38 | 12
Variable Rewards | 3 | 13 | 14.6667
LiveOps | 4 | 29 | 11.5
Onboarding | 4 | 17 | 16.75
Level Design | 5 | 25 | 14
Analytics | 4 | 18 | 12.5
TOTAL | 43 | 232
Tasks by Phase
Phase | Count | Effort (Days) | Critical | High
Phase 1 | 17 | 77 | 6 | 7
Phase 2 | 19 | 100 | 0 | 8
Phase 3 | 7 | 55 | 0 | 0

## Phase Roadmap
Implementation Roadmap
PHASE 1: Foundation (Weeks 1-6)
Goal | Fix the first 60 seconds, resolve economy inconsistencies, enable monetization infrastructure
Focus Area | Key Deliverable | Effort | KPI Target | Tasks
First Fun | Pre-placed trains + redesigned Level 1 FTUE | 8 days | Time to first reward < 30s | ML-03, ML-04
Economy Fix | Single source of truth for all numbers | 2 days | Zero cross-doc conflicts | EC-03
Premium Currency | Gold Rivets system designed + implemented | 10 days | Currency visible in Meta Hub | EC-01, EC-02
Upgrade Rebalance | T1 upgrades feel impactful | 2 days | First upgrade purchase rate > 80% | EC-06, EC-05
Onboarding | Progressive disclosure + Meta Hub tour | 10 days | D1 retention > 40% | OB-01, OB-02, OB-03
Chapter 2 Design | Full level configs for conversion chapter | 8 days | Chapter 2 completion > 50% | LD-01
Analytics | Event tracking + auto-save | 8 days | All key funnels tracked | AI-01, AI-03
Revenue Model | Revised projections with new monetization | 3 days | Realistic financial plan | MN-04
PHASE 2: Retention & Revenue (Weeks 7-14)
Goal | Add session hooks, social features, variable rewards, and Season Pass to drive D7/D30 retention and recurring revenue
Focus Area | Key Deliverable | Effort | KPI Target | Tasks
Season Pass | Engineer's Pass live with first season content | 8 days | 5% conversion in Month 1 | MN-01
Cosmetic Depth | Catalog expanded to $30+ ceiling | 12 days | 10% cosmetic purchase rate | MN-02, MN-03
Idle Layer | Railway Network passive RP generation | 8 days | 2+ daily sessions avg | SD-01, SD-02, SD-03
Social | Ghost rivals + Endless leaderboard + share | 15 days | D30 retention > 12% | SO-01, SO-02, SO-03
Variable Rewards | Bonus roll + random events + mystery chest | 13 days | Level replay rate +20% | VR-01, VR-02, VR-03
Daily Challenges | Full daily challenge system live | 8 days | 70% of active players attempt daily | LO-01
Level Variety | New objective types + Casual Mode | 10 days | Ch2-3 completion > 40% | LD-02, LD-03
Economy Tuning | A/B test framework + maintenance rebalance | 8 days | Bankrupt rate < 15% | AI-02, EC-04
PHASE 3: Scale & Polish (Weeks 15-22)
Goal | LiveOps pipeline, community features, internationalization, and long-tail engagement systems
Focus Area | Key Deliverable | Effort | KPI Target | Tasks
LiveOps | Seasonal themes + quarterly season reset | 18 days | MAU stable Month 3+ | LO-02, LO-03, LO-04
Community | Weekly challenge + alliance-lite (if warranted) | 23 days | 30% of DAU in social feature | SO-04, SO-05
Long-tail | Prestige system + career rank polish | 7 days | 10% prestige adoption | LD-05, LD-04, SD-04
International | Localization pipeline for 4 markets | 5 days | 15% revenue from non-English | AI-04

## Best Practice Ref
Best Practice Reference Table
ID | Best Practice | Summary | Iron Dominion Gap | Source
BP#1 | First Fun Principle | First 60s must deliver instant gratification via simple, self-contained mechanic | Large: 2-4 min build phase before first reward | GameMakers, GameRefinery
BP#2 | Dual-Currency Economy | Soft + Hard + Social currencies with balanced faucets/drains | Large: Only $ and RP, no premium or social currency | Lost Garden, Kallist
BP#3 | Time Compression Monetization | Speed-ups as primary revenue driver, open-ended LTV | Large: One-time $3.99, capped LTV at ~$14 | ThinkingData, DoF
BP#4 | Social/Alliance Systems | Alliance within 48hrs, daily social obligations, alliance shop | Critical: Zero social features | GameRefinery, ThinkingData
BP#5 | Hybridization | Casual mechanic + 4X depth for broader audience | Medium: Tycoon framing is good but no dedicated micro loop | GameRefinery, Naavik
BP#6 | Multi-Cadence Sessions | 3-5 daily sessions of varying length | Large: Single 10-15 min session, no quick-check flow | GameAnalytics
BP#7 | Event-Driven LiveOps | 3-5 overlapping events at all times post-launch | Large: Daily Challenges designed but not built, no other events | DoF, GameRefinery
BP#8 | Progressive Disclosure | Hide complexity for first hour, reveal over 7 days | Medium: Full UI visible from start, tutorial covers 3 levels | Last War analysis
BP#9 | Variable Rewards | Mystery chests, random events, bonus rolls | Medium: 100% deterministic rewards | Player psych research